## Sheet1
Item | Status | End | People | Notes
Phase 1: Groundwork
Match UJ to 1870 diary & assign to Erin/Ashanka |  | 2015-01-09 | MW
Print up pages of diary and review |  | 2015-01-12 | AW/MW
Go through XML transcription and add notes from XML to processing spreadsheet |  | 2015-01-13 | MW
Work through spreadsheet for patterns; share with RE/KK |  | 2015-01-16 | AW/MW
Convert final 1870 diary bits to LEAP standard |  | 2015-01-23 | AW
Identify/transcribe/proof Agnes sections of diary |  | 2015-02-04 | AW/MW/AK
encode published version of diary in basic XML |  | 2015-02-16 | AK/EC
travel to Scotland and meet with Scottish stakeholders to review progress |  | 2015-05-15 |  | Image processing was ongoing but other wise process stopped because of LEAP
Phase 2a: Critical Apparatus (Essays)
read field diary XIII, 1870 diary, UJ, and published text comparatively |  | 2015-08-20 | AW/MW/EC | focus on 1870 diary and its process of composition (FD XIII, UJ, published text); study images too
research/write essay on genealogical development of text |  | 2016-01-22 | MW(lead)/AW | need to review & borrow essay structures from 1871 diary edition
correction to Livingsotne's Composition Practices |  | 2016-03-02 | MW(lead)/AW | add paragraph about letter in diary
research/write essays on State of the Manuscript, parts I and II |  | 2016-01-29 | AW(lead)/MW
meet to discuss of historical, cultural and biographical essay |  | 2016-01-15 | AW/MW
NEH year II report due |  | 2016-02-29 | AW/MW/KK/RE
contact BL/NLS/DLC re: history of the manuscript |  | 2016-04-01 | AW
research/write essay on Livingstone and World |  | 2016-03-18 | MW(lead)/AW
revise Livingstone and World based on comments |  | 2016-06-17 | MW
research/write/revise essays on State of the Manuscript, parts III, IV, V, VI |  | 2016-07-01 | AW(lead)/AK/MW | Initial draft done; AK reviewing to finish by 6/17; Megan to finish by 6/24 (Done); AW to finish by 7/1
research/write essays on spectral image processing |  | 2016-08-01 | AW(lead)/MW/RE/KK | VS essay has started this process
Phase 2b: Glossary
generate list of key terms from diary |  | 2106-02-10 | AW
finalize list of key terms from diary |  | 2016-03-04 | AW/MW
develop glossary of key terms |  | 2016-04-08 | AW
develop glossary of key terms |  | 2016-04-08 | MW
proof glossary |  | 2016-04-15 | AW/MW
add id's to terms in TEI |  | 2016-04-18 | AM
create XML definition files |  |  | AW
get copy of 1870 FD text in Zimbabwe |  |  | MW | not done
acquire digital copies of images, illustrations, and maps needed for apparatus |  |  |  | We have everything we need via LEAP
Additional LEAP Tasks
assemble final LO image set for ingest |  | 2016-04-01 | AW | with help from Alex
finalize PDFs for archival packets |  |  | AW | involves James; waiting on him now
update LO project standards section |  |  | AW | involves Nigel
meet to discuss LEAP critical introductions |  | 2016-02-29
create Livingstone Online site guide |  |  | AW
review and update other LEAP documentation as necessary |  | 2016-07-01 | AW
review and update other LO essays as necessary |  | 2016-07-01 | AW
write theoretical essay framing Livingstone Online project |  | all work finished no later than July 1, 2016 | MW/AW | MW to write by 6/20/16 (DONE 6/14), AW revise by 6/24/16, MW finalize by 7/1/16 (DONE) and up on site by early July 2016
write essay on LO site design |  | 2016-07-15 | AA/AW/MW | Needs to be done, dusted, and on LO *before* to August 1
formal first edition of new LO released |  | 2016-08-01 | AW/MW | non-negotiable date
write LEAP critical introductions (diaries) |  | 2016-08-01 | MW | Detailed breakdown at the bottom of the page. Although this technically should go in the new section below, let's leave it here to keep it prioritized as this is a task that needs to get done ASAP given everything else we have to do in fall 2016 & spring 2017.
Field Diary Introductions
FD I | xslt | 2016-08-01 | MW | drafted MW; reviewed AW; revised MW
FD II | xslt | 2016-08-01 | MW | drafted MW; reviewed AW; revised MW
FD III | xslt | 2016-08-01 | MW | drafted MW; reviewed AW; nothing else needed
FD IV | xslt | 2016-08-01 | MW | drafted MW; reviewed AW; revised MW
FD V | xslt | 2016-08-01 | MW | drafted MW; reviewed AW; revised MW
FD VI | xslt | 2016-08-01 | MW | drafted MW; reviewed AW
FD VII | xslt | 2016-08-01 | MW | drafted MW; reviewed AW
FD X | xslt | 2016-08-01 | MW | drafted MW; reviewed AW
FD XIV | xslt | 2016-08-01 | MW | drafted MW; reviewed AW
FD XV | xslt | 2016-08-01 | MW | drafted MW; reviewed AW
FD XVI | xslt | 2016-08-01 | MW | drafted MW; reviewed AW
FD XVII | xslt | 2016-08-01 | MW | drafted MW; reviewed AW
Phase 3: Spectral Imaging Development
conclude processing spectral images |  |  | RE
conclude processing spectral images |  |  | KK
additional processing |  | 2016-04-01 | KK | registered image processing (red-green recto-verso; smearing)
contact BL re: spectral images of pages I-IV |  | 2016-04-01 | AW | failed
create preliminary version of archive with core data |  | 2016-03-15 | AW | done; just waiting on a few corrections from Keith
contact Roger and Keith for descriptions of processing |  | 2016-05-01 | MW
additional processing |  |  | RE | additional image set; may not be realized
additional processing |  |  | KK | processing for ink types; not fully realized
Phase 4: 1870 FD Interface & Data Development
travel to Los Angeles to plan interface development with UCLA staff; deliver lecture to UCLA faculty and students on the proposed edition
training on using Drupal interface for development |  | 2016-08-01 | MW | AW will provide support/training as needed
create image data generator & Drupal template |  | 2016-08-01 | AW
UNL ORED grant report due |  | 2016-08-01 | AW
draft proposal/contract for Livingstone Museum |  | 2016-08-01 | AW
develop XSLT for edition interface |  | 2016-08-01 | AW
write essay on ASI |  | Aug.-Sept. 2016 | AK/AW/MW
assemble project documentation |  | Sept. 2016 | AW/LG
write project introduction |  | Sept. 2016 | AW
LEAP NEH report for year 3 due |  | Sept. 2016 | AW/MW/MT/HB
XSLT for LLJ |  | 2016-10-01 | AW
XSLT for UJ |  | 2016-10-01 | AW
generate metadata/build archival packets/create data directories |  | 2016-10-01 | AW/MW/RE/KK | with Doug Emery
create NEH compliance matrix |  | 2016-10-01 | LG/MW
interface development (create webpages) |  | Sept.-Oct. 2016 | MW (lead) | more labor-intensive than it seems; AW will provide support as needed
create bibliography / add to Zotero / create Drupal page |  | 2016-10-01 | MW/LG
write documentation intro |  | 2016-10-01 | AW/MW
create 1870 FD citation guide |  | 2016-10-01 | AW/MW
update citations on all essays |  | 2016-10-01 | AW/MW
write project history |  | 2016-10-01 | AW/MW
create 1870 FD site guide |  | 2016-11-01 | AW
add illustrative images for critical essays |  | Oct.-Nov. 2016 | AW
1. Create two new Drupal Content types |  | 2016-10-01 | NB
2. Implement spectral content model |  | Oct.-Nov. 2016 | NB
3. Update Batch Upload/Replace |  | Oct.-Nov. 2016 | NB
4. Implement alternate TEI/XSL support |  | Oct.-Nov. 2016 | NB
5. Impement multiple XSLT viewer |  | Oct.-Nov. 2016 | NB
6. Spectral viewer development |  | Oct.-Nov. 2016 | NB
beta edition of 1870 FD site released |  | 2016-11-16 | AW/MW
travel to UK to review project results with stakeholders; deliver lectures at stakeholder institutions: Oxford, Edinburgh, Belfast |  | 2016-11-01 | AW/MW/RE/KK | Week 3 of November
write final segment of project history |  | 2016-12-01 | AW(lead)/MW
final NEH report & compliance matrix on 1870 FD project due |  | 2017-03-31 | AW/MW/RE/KK
research/write/revise essay on Livingstone, 1870, Central Africa |  | Nov.-Mar. 2016-17 | AW(lead)/MW/JL | Aiming to finish by March 1, including put online & add images
final edition of 1870 FD site released |  | 2017-03-31 | AW/MW/RE/KK/AK | Finishing the Africa essay finishes this
submit 1870 FD to NINES |  | Sum. 2017 | AW | Submitted on May 30 & acknowledged June 13
Phase 5: 1871 FD / FDs & UJ / LEAP close out
integrate UJ |  | 2016-10-01 | HB
develop XSLT for FDs |  | Nov.-Dec. 2016 | AW/JL/KS
final proofing review of UJ |  | Nov.-Dec. 2016 | MW
write UJ intro |  | Nov.-Feb. 2016 | MW
check all legacy XML for formatting |  | 2017-03-01 | LG
convert published Last Journals to XML |  | 2017-03-31 | MW/AW
proof converted Last Journals against original images |  | 2017-05-01 | LG
add images to UJ & FDs edition |  | 2017-06-01 | AW
create "Death of Livingstone" bonus page |  | 2017-06-01 | AW
final tweaking of LJs |  | 2017-06-01 | MW/AW
transcribe FD XII, "second" UJ pages, and 1873 fragment |  | 2017-06-01 | HB/AW
develop XSLT for UJ |  | 2017-06-01 | AW
create scope of the edition page |  | 2017-06-15 | AW/MW
write short field diary overviews |  | 2017-06-15 | MW/AW
write overall intro to field diaries |  | 2017-06-15 | MW/AW
create acknowledgments page |  | 2017-06-15 | AW/MW
create three bonus texts page |  | 2017-06-15 | AW/MW
write introduction to final diaries/journals critical edition project |  | 2017-06-15 | MW | circa 1 page, similar to 1870 FD intro
add images to long FDs essay, intro, acknow, scope, & 3 bonus text pages |  | 2017-06-15 | AW
build beta edition (build packets, links, etc.) |  | 2017-06-24 | AW
release beta edition of UJ & FDs |  | 2017-06-24 | AW/MW/NB
random site corrections |  | 2016-12-01 | AW
integrate Bambarre letter project into LO |  | 2017-02-01 | AW
review integrated Bambarre |  | 2017-03-01 | MW
integrate 1871 FD project into LO |  | 2017-04-15 | AW
assemble post-beta project documentation |  | 2017-04-01 | AW
review integrated 1871 FD |  | 2017-04-01 | MW
update/corr LO bibliographies |  | 2017-05-15 | AW/JL
redo site anchors |  | 2017-06-15 | AW
redo centered image captions |  | 2017-06-15 | AW
complete outstanding XML work (legacy letters) |  | 2017-07-01 | MW/AW/SF/HB/MB/JL/KS
LEAP & Final MS. closeouts
review standards page & create other documentation |  | 2017-11-01 | NB/AW
conclude LEAP history post-beta launch |  | 2017-11-01 | AW(lead)/MW
review and correct UJ word lists & make UJ corrections | see below | 2017-11-01 | HB/MW/AW | will continue past beta release
final review of word lists |  | 2017-11-01 | AW
write Livingstone Online instruction manual |  | 2017-11-01 | AW(lead)/MW
second edition of Livingstone Online released |  | 2017-11-01 | AW
develop Browse by Geolocation / other final site work, incl RDF |  | 2017-11-01 | AW/NB
first edition of Final Manuscripts released |  | spring 2018 | AW | to do: B&W TEI text. done: update download docs; justify last LJ par lines; other LJ corrs; UJ par gaps (54).
Reporting, Peer-Review and Dissemination
final NEH report on LEAP |  | fall 2017 | AW/MW
solicit reviews of 1870 FD, final ms., and LO from journals |  | fall 2017 | AW/MW
distribute 1870 FD & final ms. press releases/academic announcements |  | fall 2017 | AW/MW | reach out to journalists, contact specialists, promote on various listservs and newsletters
submit Final Manuscripts to NINES |  | spring 2018 | AW
bloc |  |  | HB(lead)/AW
country |  |  | HB(lead)/AW
quote |  |  | HB(lead)/AW
term |  | 2017-01-01 | HB(lead)/AW
region | 444 | 2017-01-01 | HB(lead)/AW
consistency check: colors, linebreaks, letters |  | Feb.-Mar. 2017 | HB(lead)/AW
add Megan's corrections |  | 2017-06-01 | MW
foreign | 657 | Sum. 2017 | HB(lead)/AW
orgName | 1122 | Sum. 2017 | HB(lead)/AW
settlement | 1114 | 2017-11-01 | HB(lead)/AW | HB will normalize; AW will finalize
geogName | 1724 | 2017-11-01 | HB(lead)/AW | HB will normalize; AW will finalize
persName | 1975 | 2017-11-01 | HB(lead)/AW | HB will normalize; AW will finalize